## Punch List
Location | Category | Item / Description | Priority | Status | Assigned To / Contractor | Est. Cost ($) | Notes | How to use: fill columns A-H from row 2 down (row 2 is an example - overwrite it). Location, Category, Priority, and Status have dropdowns fed by the Lists sheet. Sort by Location then Category (Data > Sort) to group the list. Est. Cost is user-entered.
Kitchen | Electrical | Install power receptacles on both sides of the kitchen island |  | Not Started
Kitchen | Electrical | Replace pendant light bulbs with rounded white globe bulbs |  | Not Started |  |  | Bulbs need to be purchased first
Family Room | Electrical | Put all interior lights on dimmers - the light in front of the bathroom is currently not on a dimmer |  | Not Started
Family Room | Electrical | Change exterior light from dimmer to standard on/off switch |  | Not Started |  |  | Currently on a dimmer
Family Room | Painting | Repaint to cover up plaster touch-ups |  | Not Started
Family Room | Windows & Doors | Remove tape from top of the door between bedroom and family room, including the rail guide at the top |  | Not Started
Sitting Room | Electrical | Find and install slope-ceiling adapter from Wayfair |  | Not Started |  |  | Adapter needs to be located first
Sitting Room | Electrical | Install reading light in the corner |  | Not Started
Powder Room | General Contractor | Set up powder room (general) |  | Not Started
Downstairs Bathroom | Drywall | Fill in sheetrock in the area under the medicine cabinet |  | Not Started
Downstairs Bathroom | General Contractor | Remove protective film from the medicine cabinet - still on, making the mirror look dark |  | Not Started
Downstairs Bathroom | Painting | Clean up pencil lines above the medicine cabinet |  | Not Started
Hallway | Electrical | Change front foyer exterior light from dimmer to standard on/off switch |  | Not Started |  |  | Front foyer
Hallway | Painting | Apply another coat of stain to handrail - darker, to closer match the treads |  | Not Started
Linen Closet | Carpentry | Install closet poles |  | Not Started |  |  | Poles expected to arrive Mon Jul 27
Laundry Room | Carpentry | Install tools on the upper cabinet |  | Not Started |  |  | Arriving Mon Jul 27
Upstairs Bathroom | Electrical | Fix vanity light - flickers when turned on |  | Not Started
Upstairs Bathroom | Electrical | Put both light switches on occupancy sensors - remove the switch with the 60-minute timer |  | Not Started
Upstairs Bathroom | Electrical | Replace 2700K vanity bulb with 4000K (cool white), 60W equivalent - current warm color not liked |  | Not Started |  |  | Buy: 4000K, ~800 lumens (60W equivalent), E26 base. Current bulb is only 450 lm (~40W equiv)
Upstairs Bathroom | General Contractor | Install medicine cabinet |  | Not Started |  |  | Cabinet arriving Mon Jul 27
Concierge Bathroom | Electrical | Put both switches on vacancy sensors |  | Not Started |  |  | Dimmer already removed
Primary Bedroom | Electrical | Replace on/off switch with Aqara dimmer |  | Not Started |  |  | Aqara dimmer already purchased
Bedroom 1 | Electrical | Install lighting inside closet |  | Not Started
Bedroom 2 | Electrical | Install lighting inside closet |  | Not Started
Attic | HVAC | Confirm HVAC is working - clear the error still showing on the HVAC/thermostat screen |  | Not Started
Attic | HVAC | Turn on whole-home dehumidifier, set to 45%, and confirm working |  | Not Started
Garage | Carpentry | Install shelving on north wall of garage |  | Not Started
Garage | Carpentry | Install one kitchen cabinet to the right of the existing one |  | Not Started
Garage | Electrical | Install missing plate over light switch (near garage door) |  | Not Started
Garage | Garage Door | Service garage door - very shaky as it starts, creaky as it stops |  | Not Started

## Lists
Locations | Categories | Statuses | Priorities | Add new locations/categories here as the project grows - dropdowns read the whole column.
Whole House | General Contractor | Not Started | High
Exterior | Electrical | In Progress | Medium
Living Room | Plumbing | Blocked | Low
Family Room | HVAC | Done
Dining | Carpentry
Kitchen | Drywall
Hallway | Painting
Bath 1 | Flooring
Powder Room | Tile
Linen Closet | Windows & Doors
Study/Den | Roofing
Sitting Room | Landscaping
Laundry Room | Appliances
Upstairs Bathroom | Other
Concierge Bathroom | Garage Door
Primary Bedroom
Bedroom 1
Bedroom 2
Attic
Garage
Downstairs Bathroom

## Summary
461 Anderson Street - Punch List Summary
Total items | 30
Not Started | 30
In Progress | 0
Blocked | 0
Done | 0
Total est. cost | 0